## Schedules
Schedule - List - **Remodel - Kitchen** (exported on Dec 13, 2021)
ID # | Title | Marked Complete | Phase | Dur. | Start | End | Assigned To | Confirm Accepted Count | Confirm Pending Count | Confirm Declined Count | Pred | Pred 1 Lag
1 | Demo | FALSE |  | 2 | 2015-03-02 | 2015-03-03 | N/A | 0 | 0 | 0
2 | Install dust protection | FALSE |  | 1 | 2015-03-02 | 2015-03-02 | N/A | 0 | 0 | 0
3 | Frame | FALSE |  | 2 | 2015-03-04 | 2015-03-05 | N/A | 0 | 0 | 0 | 1 FS | 0
4 | Framewalk | FALSE |  | 1 | 2015-03-04 | 2015-03-04 | N/A | 0 | 0 | 0 | 1 FS | 0
5 | Cabinet measure | FALSE |  | 1 | 2015-03-06 | 2015-03-06 | N/A | 0 | 0 | 0 | 3 FS | 0
6 | Rough Plumbing | FALSE |  | 2 | 2015-03-06 | 2015-03-09 | N/A | 0 | 0 | 0 | 3 FS | 0
7 | Rough electrical | FALSE |  | 2 | 2015-03-10 | 2015-03-11 | N/A | 0 | 0 | 0 | 6 FS | 0
8 | Frame inspection | FALSE |  | 1 | 2015-03-12 | 2015-03-12 | N/A | 0 | 0 | 0 | 7 FS | 0
9 | Install Insulation | FALSE |  | 1 | 2015-03-12 | 2015-03-12 | N/A | 0 | 0 | 0 | 7 FS | 0
10 | Install Sheetrock | FALSE |  | 2 | 2015-03-13 | 2015-03-16 | N/A | 0 | 0 | 0 | 8 FS | 0
11 | Sheetrock Inspection | FALSE |  | 1 | 2015-03-17 | 2015-03-17 | N/A | 0 | 0 | 0 | 10 FS | 0
12 | Tape, Top, Texture | FALSE |  | 4 | 2015-03-18 | 2015-03-23 | N/A | 0 | 0 | 0 | 11 FS | 0
13 | Install doors,casing | FALSE |  | 1 | 2015-03-24 | 2015-03-24 | N/A | 0 | 0 | 0 | 12 FS | 0
14 | Interior paint | FALSE |  | 3 | 2015-03-25 | 2015-03-27 | N/A | 0 | 0 | 0 | 13 FS | 0
15 | Install cabinets | FALSE |  | 3 | 2015-03-30 | 2015-04-01 | N/A | 0 | 0 | 0 | 14 FS | 0
16 | Counter top template | FALSE |  | 1 | 2015-04-02 | 2015-04-02 | N/A | 0 | 0 | 0 | 15 FS | 0
17 | Install flooring | FALSE |  | 3 | 2015-04-02 | 2015-04-06 | N/A | 0 | 0 | 0 | 15 FS | 0
18 | Install counter tops | FALSE |  | 1 | 2015-04-03 | 2015-04-03 | N/A | 0 | 0 | 0 | 16 FS | 0
19 | Install backsplsh | FALSE |  | 2 | 2015-04-06 | 2015-04-07 | N/A | 0 | 0 | 0 | 18 FS | 0
20 | Install baseboard | FALSE |  | 1 | 2015-04-07 | 2015-04-07 | N/A | 0 | 0 | 0 | 17 FS | 0
21 | Finish electrical | FALSE |  | 2 | 2015-04-08 | 2015-04-09 | N/A | 0 | 0 | 0 | 19 FS | 0
22 | Finish plumbing | FALSE |  | 1 | 2015-04-10 | 2015-04-10 | N/A | 0 | 0 | 0 | 21 FS | 0
23 | Texture touch up | FALSE |  | 1 | 2015-04-10 | 2015-04-10 | N/A | 0 | 0 | 0 | 21 FS | 0
24 | Appliance Install | FALSE |  | 1 | 2015-04-13 | 2015-04-13 | N/A | 0 | 0 | 0 | 22 FS | 0
25 | Install door hardware | FALSE |  | 1 | 2015-04-13 | 2015-04-13 | N/A | 0 | 0 | 0 | 22 FS | 0
26 | Cabinet touch up | FALSE |  | 1 | 2015-04-14 | 2015-04-14 | N/A | 0 | 0 | 0 | 25 FS | 0
27 | Paint baseboards, touch up | FALSE |  | 1 | 2015-04-14 | 2015-04-14 | N/A | 0 | 0 | 0 | 25 FS | 0
28 | Final inspection | FALSE |  | 1 | 2015-04-15 | 2015-04-15 | N/A | 0 | 0 | 0 | 27 FS | 0
29 | Completion items | FALSE |  | 5 | 2015-04-16 | 2015-04-22 | N/A | 0 | 0 | 0 | 28 FS | 0
30 | Final Clean | FALSE |  | 1 | 2015-04-23 | 2015-04-23 | N/A | 0 | 0 | 0 | 29 FS | 0
31 | Remove Portable Toilet | FALSE |  | 1 | 2015-04-23 | 2015-04-23 | N/A | 0 | 0 | 0 | 29 FS | 0